## Slide 1
KARTA CONSULTING GROUP
AI strategy · Weekly status · September 12, 2026
AI strategy: weekly status
Week of September 7 to 11, 2026 · first weekly status of the 90-day push
OVERALL
GREEN
One workstream Yellow: platform accounts and IT consent.
ACCOMPLISHED THIS WEEK
Legend workspace live September 8. First Weekly Status approved and the client deck built September 9.
Blank template with a non-technical setup screen. A new engagement stands up in about ten minutes.
Cold test under way: two colleagues setting up a second workspace unassisted to expose the gaps.
Karta GitHub and Google Cloud accounts approved September 9. Setup request sent to Marianna.
One self-contained code repository with a documented operating model, solution design and showcase.
PLANNED NEXT WEEK
Weekly Status every Friday on Legend and the second engagement.
Fold in the cold-test findings. Re-check the Legend SharePoint link and stage dates.
Karta GitHub organization and Cloud account set up. Move the repository and the assembly service.
Follow up with IT on Microsoft Entra admin consent.
Ethan's review of the status contracts and vocabulary.
DECISIONS, RISKS AND WATCH ITEMS
DECISION
Confirm the 90-day release dates: October 3, October 31, December 5, scale review December 12.
DECISION
Name the second pilot engagement and its reviewer.
RISK
Entra admin consent pending with IT. Until granted, reviewers save decks to SharePoint themselves and connector sign-in stays deferred. Interim mode is running.
WATCH
Practitioner time to run Weekly Status each week alongside client work.
WORKSTREAMS
STATUS
WHERE IT STANDS
Engagement Workspace · Project Status Reporting
GREEN
Live for Legend. Weekly Status v1 approved and deck built. Setup, Home, Weekly Status, Config and pilot measures in place.
Foundations Package · requirements to mockups
GREEN
Mockup Generator in use. BRD, Design Deck and Integration Matrix skills in progress. Meeting closeout into requirements is the next piece.
Governance and operating model
GREEN
Capability catalog with owners and readiness labels. Named approvals recorded. Idea, Invest, Pilot, Scale pipeline defined. Protected main, pull requests and CI documented.
Platform, accounts and IT
YELLOW
GitHub and Cloud accounts approved, setup week of September 14. Entra admin consent pending. Cloud spend to date $0.36 against a $300 credit.
Skills and practitioner enablement
GREEN
Complete: Estimator, Win Story, Industry One Pager, RFP Questions, Status Decks, RAID Log updates, Granola to Asana follow-ups. Six more in progress across Foundations and Build.
90-DAY PUSH · ONE RELEASE A MONTH · DATES PROPOSED, TO CONFIRM TODAY
Sep 12
Status 1
today
Oct 3
Release 1 · Foundation
Two engagements, Ask Claude, catalog
Oct 31
Release 2 · Context
Granola and Harvest feed attention
Dec 5
Release 3 · Beyond status
Sprint review prep, Foundations piece
Dec 12
Scale review
what to scale, change, or stop
Notes: First weekly status of the AI program, September 12, 2026. Overall Green with one Yellow workstream. Accomplished: Legend workspace live September 8. First Weekly Status approved and the client deck built September 9. Blank template with a non-technical setup screen. A new engagement stands up in about ten minutes. Cold test under way: two colleagues setting up a second workspace unassisted to expose the gaps. Karta GitHub and Google Cloud accounts approved September 9. Setup request sent to Marianna. One self-contained code repository with a documented operating model, solution design and showcase. Planned: Weekly Status every Friday on Legend and the second engagement. Fold in the cold-test findings. Re-check the Legend SharePoint link and stage dates. Karta GitHub organization and Cloud account set up. Move the repository and the assembly service. Follow up with IT on Microsoft Entra admin consent. Ethan's review of the status contracts and vocabulary. Decision: Confirm the 90-day release dates: October 3, October 31, December 5, scale review December 12. Decision: Name the second pilot engagement and its reviewer. Risk: Entra admin consent pending with IT. Until granted, reviewers save decks to SharePoint themselves and connector sign-in stays deferred. Interim mode is running. Watch: Practitioner time to run Weekly Status each week alongside client work. Workstreams: Engagement Workspace · Project Status Reporting is Green. Live for Legend. Weekly Status v1 approved and deck built. Setup, Home, Weekly Status, Config and pilot measures in place. Foundations Package · requirements to mockups is Green. Mockup Generator in use. BRD, Design Deck and Integration Matrix skills in progress. Meeting closeout into requirements is the next piece. Governance and operating model is Green. Capability catalog with owners and readiness labels. Named approvals recorded. Idea, Invest, Pilot, Scale pipeline defined. Protected main, pull requests and CI documented. Platform, accounts and IT is Yellow. GitHub and Cloud accounts approved, setup week of September 14. Entra admin consent pending. Cloud spend to date $0.36 against a $300 credit. Skills and practitioner enablement is Green. Complete: Estimator, Win Story, Industry One Pager, RFP Questions, Status Decks, RAID Log updates, Granola to Asana follow-ups. Six more in progress across Foundations and Build. The 90-day dates are proposed and should be confirmed in this meeting. Each release is reviewed at month end; contents are the working plan.